## Product Backlog
Project Name | SAUCEDEMO
Client
Created By | Durgesh Kumar Prajapati
Creation Date | 05.11.2024
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
| Us_01 | Validate the login functionality with first character should be uppercase character of username and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_02 | Validate the login functionality by removing all special character from the username and using the correct password. | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| 0 | Validate the login functionality when a user enter a lowercase character of username and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_04 | To validate the login functionality except first character all the character should be uppercase from username and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_05 | Validate the login functionality when a user enter valid username and valid password | User Should able to see home page | Done | 1.Enter valid username &valid password 2.Click on login button 3.User should able to see home page
| Us_06 | Validate the login functionality of all special character of of username and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_07 | Validate the login functionality username should be empty and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_08 | Validate the login functionality all numbers of username and correct password | show the error message | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_09 | Validate the login functionality correct username and password should be only three character | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_10 | Validate the login functionality correct username and password should be empty | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_11 | Validate the login functionality correct username and password should be numeric | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_12 | Validate the login functionality correct username and password should be special character | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_13 | Validate the login functionality correct username and remove the special character from the password | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_14 | Validate the login functionality correct username and user enter password only 8 character | show the error message | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_15 | Validate the behaviour of login page when a user enter the username and password should be valid | User Should able to see product page | Done | 1.Enter valid username &valid password 2.Click on login button 3.User should able to see home page
| Us_16 | To validate that page title of home page of swaglabs website is "Swag labs" | Proper Page Title "Swag Labs "are displayed on title bar. | Done | 1.Login to Swag Labs with a valid username and password. 2. Click on any existing Product name displayed on product page. 3. Check the Page Title 'Product Display' page . 4.Check the Page Title.
| Us_17 | To validate that user can see the list of Products available on homepage of swaglabs website. | The product page should display a list of available products. | Done | 1.Login to Swag Labs with a valid username and password. 2.The product page will display.
| Us_18 | To validate that product images are loading correctly on homepage of Swag Labs website. | The product page should display a image of products. | Done | 1.Login to Swag Labs with a valid username and password. 2.The product image will be display on product page.
| Us_19 | To validate that after clickinng on product name or image, Product Details Page will open. | The product details page is displayed with information like description, price, and add to cart button. | Done | 1.Login to Swag Labs with a valid username and password. 2.The products will be display on product page. 3.Click on any product. 4.Product details will be display on next page.
| Us_20 | To that validate Products available on home page should be Sorted according to given sorting option from the available dropdown. | The products are sorted according to the sorting option from the available dropdown. | Done | 1.Login to Swag Labs. 2.Verify the default sorting of products . 3.Select a different sorting option from the available dropdown

## Sprint Planning
Project Name | SAUCEDEMO
Client
Created By | Durgesh Kumar Prajapati
Attendees | Durgesh Kumar Prajapati
Creation Date | 14/06/2024
Epic | User Story ID | Feature/Title | User Story | Sprint | Status | Acceptance Creteria
Epic_1 | Us_01 | Validate the login functionality with first character should be uppercase character of username and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_02 | Validate the login functionality by removing all special character from the username and using the correct password. | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_03 | Validate the login functionality when a user enter a lowercase character of username and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_04 | Validate the login functionality except first character all the character should be uppercase from username and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_05 | Validate the login functionality when a user enter valid username and valid password | User Should able to see home page | 1 | Done | 1.Enter valid username &valid password 2.Click on login button 3.User should able to see home page
| Us_06 | Validate the login functionality of all special character of of username and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_07 | Validate the login functionality username should be empty and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_08 | Validate the login functionality all numbers of username and correct password | show the error message | 1 | Done | 1.Enter invalid username &valid password 2.Click on login button 3.A pop up box of an error message
| Us_09 | Validate the login functionality correct username and password should be only three character | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_10 | Validate the login functionality correct username and password should be empty | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_11 | Validate the login functionality correct username and password should be numeric | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_12 | Validate the login functionality correct username and password should be special character | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_13 | Validate the login functionality correct username and remove the special character from the password | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_14 | Validate the login functionality correct username and user enter password only 8 character | show the error message | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button 3.A pop up box of an error message
| Us_15 | Validate the behaviour of login page when a user enter the username and password should be valid | User Should able to see product page | 1 | Done | 1.Enter valid username &valid password 2.Click on login button 3.User should able to see home page
| Us_16 | To Validate that page title of home page of swaglabs website is "Swag labs" | Proper Page Title "Swag Labs "are displayed on title bar. | 1 | Done | 1.Login to Swag Labs with a valid username and password. 2. Click on any existing Product name displayed on product page. 3. Check the Page Title 'Product Display' page . 4.Check the Page Title.
| Us_17 | To Validate that user can see the list of Products available on homepage of swaglabs website. | The product page should display a list of available products. | 1 | Done | 1.Login to Swag Labs with a valid username and password. 2.The product page will display.
| Us_18 | To Validate that product images are loading correctly on homepage of Swag Labs website. | The product page should display a image of products. | 1 | Done | 1.Login to Swag Labs with a valid username and password. 2.The product image will be display on product page.
| Us_19 | To validate that after clickinng on product name or image, Product Details Page will open. | The product details page is displayed with information like description, price, and add to cart button. | 1 | Done | 1.Login to Swag Labs with a valid username and password. 2.The products will be display on product page. 3.Click on any product. 4.Product details will be display on next page.
| Us_20 | To that validate Products available on home page should be Sorted according to given sorting option from the available dropdown. | The products are sorted according to the sorting option from the available dropdown. | 1 | Done | 1.Login to Swag Labs. 2.Verify the default sorting of products . 3.Select a different sorting option from the available dropdown

## Test scenarios
Project Name | Saucedemo
Module Name | Saucedemo_Test_cases
Requirement Number | REQ001
Test case Type | Functionality , Usability , Integration Testings
Reference Doccument | NA
Pre-condition | Saucedemo URL should be accessible
Test Data | https://www.saucedemo.com/
Test Senario number | Description | Test Scenario Type | TE Name
User Story 1
THS_01 | Validate the login functionality with first character should be uppercase character of username and correct password | Validate | Durgesh kr Prajapati
THS_02 | Validate the login functionality by removing all special character from the username and using the correct password. | Functionality Testing | Durgesh kr Prajapati
THS_03 | Validate the login functionality when a user enter a lowercase character of username and correct password | Functionality Testing | Durgesh kr Prajapati
THS_04 | Validate the login functionality except first character all the character should be uppercase from username and correct password | Functionality Testing | Durgesh kr Prajapati
THS_05 | Validate the login functionality when a user enter valid username and valid password | Functionality Testing | Durgesh kr Prajapati
THS_06 | Validate the login functionality of all special character of of username and correct password | Functionality Testing | Durgesh kr Prajapati
THS_07 | Validate the login functionality username should be empty and correct password | Functionality Testing | Durgesh kr Prajapati
THS_08 | Validate the login functionality all numbers of username and correct password | Functionality Testing | Durgesh kr Prajapati
THS_09 | Validate the login functionality correct username and password should be only three character | Functionality Testing | Durgesh kr Prajapati
THS_10 | Validate the login functionality correct username and password should be empty | Functionality Testing | Durgesh kr Prajapati
THS_11 | Validate the login functionality correct username and password should be numeric | Functionality Testing | Durgesh kr Prajapati
THS_12 | Validate the login functionality correct username and password should be special character | Functionality Testing | Durgesh kr Prajapati
THS_13 | Validate the login functionality correct username and remove the special character from the password | Functionality Testing | Durgesh kr Prajapati
THS_14 | Validate the login functionality correct username and user enter password only 8 character | Functionality Testing | Durgesh kr Prajapati
THS_15 | Validate the behaviour of login page when a user enter the username and password should be valid | Functionality Testing | Durgesh kr Prajapati

## Test cases
TE Name | Test case number | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date | DEFECT NO
Durgesh Kr Prajapati | TC_01 | Validate the login functionality with first character should be uppercase character of username and correct password | validate the behavior of the login functionality when a user enter username with first character should be uppercase and correct password | 1.Open the saucedemo application 2. Enter first character should be uppercase in username 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | Medium | High | Durgesh kr Prajapati | pass | 14/10/2024 | 14/10/2024
UserID : Standard_user Password:secret_sauce
Durgesh Kr Prajapati | TC_02 | Validate the login functionality by removing all special character from the username and using the correct password. | validate the behavior of the login functionality by removing all speical character from the username and using correct password | 1.open the saucedemo application 2. Enter username without special character 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | Medium | High | Durgesh kr Prajapati | pass | 14/10/2024 | 14/10/2024
UserID: standarduser Password:secret_sauce
Durgesh Kr Prajapati | TC_03 | Validate the login functionality when a user enter a lowercase character of username and correct password | Validate the behavior of the login functionality by enter a lowercase character of username and correct password | 1.open the saucedemo application 2. Enter lowercase character of username 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | User Should able to see product page | show the error message | Low | Medium | Durgesh kr Prajapati | Fail | 14/10/2024 | 14/10/2024 | TC_01_DT_001
UserID: ababababa Password:secret_sauce
Durgesh Kr Prajapati | TC_04 | Validate the login functionality except first character all the character should be uppercase from username and correct password | Validate the behavior of the login functionality except first character all the characters should be uppercase from username and correct password | 1.open the saucedemo application 2. Enter username except first character all the characters should be uppercase 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | Low | Medium | Durgesh kr Prajapati | pass | 14/10/2024 | 14/10/2024
UserID: sTANDARD_USER Password:secret_sauce
Durgesh Kr Prajapati | TC_05 | Validate the login functionality when a user enter valid username and valid password | Validate the behavior when a user enter valid username and password | 1.open the saucedemo application 2. Enter valid username 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 14/10/2024 | 14/10/2024
UserID: standard_user Password:secret_sauce
Durgesh Kr Prajapati | TC_06 | Validate the login functionality of all special character of username and correct password | Validate the behavior when a user enter all special character of username and correct password | 1.open the saucedemo application 2. Enter username should be special character 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | Medium | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: #$%^&@&*_$% Password:secret_sauce
Durgesh Kr Prajapati | TC_07 | Validate the login functionality username should be empty and correct password | Validate the behavior when a user doesnot username in the field and correct password | 1.open the saucedemo application 2. Empty username 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: Password:secret_sauce
Durgesh Kr Prajapati | TC_08 | Verify the login functionality all numbers of username and correct password | Validate the behavior when a user enter all numbers of username and correct password | 1.open the saucedemo application 2. Empty username should be number 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | Error message | show the error message | Medium | Medium | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: 9994566789 Password:secret_sauce
Durgesh Kr Prajapati | TC_09 | Verify the login functionality correct username and password should be only three character | Validate the behavior when a user enter correct username and password should be only three character | 1.open the saucedemo application 2. Enter valid username 3.Enter only three character of password. 4.Click on login button. | link:https://www.saucedemo.com/ | Error message | show the error message | Low | Low | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: standard_user Password:abc
Durgesh Kr Prajapati | TC_10 | Verify the login functionality correct username and password should be empty | Validate the behavior when a user enter correct username and password should be empty | 1.open the saucedemo application 2. Enter valid username 3.Empty password. 4.Click on login button. | link:https://www.saucedemo.com/ | User Should be able to see product page | show the error message | High | High | Durgesh kr Prajapati | Fail | 15/10/2024 | 15/10/2024 | TC_03_DT_002
UserID: standard_user Password:
Durgesh Kr Prajapati | TC_11 | Verify the login functionality correct username and password should be numeric | Validate the behavior when a user enter correct username and password should be numeric | 1.open the saucedemo application 2. Enter valid username 3.Enter password should be numeric. 4.Click on login button. | link:https://www.saucedemo.com/ | Error message | show the error message | Medium | Medium | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: standard_user Password:123456789
Durgesh Kr Prajapati | TC_12 | Validate the login functionality correct username and password should be special character | Validate the behavior when a user enter correct username and password should be special character | 1.open the saucedemo application 2. Enter valid username 3.Enter password should be special character. 4.Click on login button. | link:https://www.saucedemo.com/ | Error message | show the error message | Medium | Medium | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: standard_user Password: $#%^&*()_@
Durgesh Kr Prajapati | TC_13 | Validate the login functionality correct username and remove the special character from the password | Validate the behavior when a user enter correct username and password without speical character | 1.open the saucedemo application 2. Enter valid username 3.Enter password without special character. 4.Click on login button. | link:https://www.saucedemo.com/ | User Should able to see product page | show the error message | Medium | High | Durgesh kr Prajapati | Fail | 15/10/2024 | 15/10/2024 | TC_03_DT_003
UserID: standard_user Password: secretsauce
Durgesh Kr Prajapati | TC_14 | Validate the login functionality correct username and user enter password only 8 character | Validate the behavior when a user enter correct username and password should be only 8 character | 1.open the saucedemo application 2. Enter valid username 3.Enter password should be 8 characters. 4.Click on login button. | link:https://www.saucedemo.com/ | User Should able to see product page | show the error message | Low | Low | Durgesh kr Prajapati | Fail | 15/10/2024 | 15/10/2024 | TC_03_DT_004
UserID: standard_user Password: secretsa
Durgesh Kr Prajapati | TC_15 | Validate the behaviour of login page when a user enter the username and password should be valid | Validate the behavior when a user enter the valid username and password | 1.open the saucedemo application 2. Enter valid username 3.Enter valid password. 4.Click on login button. | link: https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID: standard_user Password:secret_sauce
|  |  |  | 1.Login to Swag Labs with a valid username and password. 2. Click on any existing Product name displayed on product page. 3. Check the Page Title 'Product Display' page . 4.Check the Page Title. | link:https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID:standard_user Password:secret_sauce
|  |  |  | 1.Login to Swag Labs with a valid username and password. 2.The product page will display. | link:https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID:standard_user Password:secret_sauce
|  |  |  | 1.Login to Swag Labs with a valid username and password. 2.The product image will be display on product page. | link:https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID:standard_user Password:secret_sauce
|  |  |  | 1.Login to Swag Labs with a valid username and password. 2.The products will be display on product page. 3.Click on any product. 4.Product details will be display on next page. | link:https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID:standard_user Password:secret_sauce
|  |  |  | 1.Login to Swag Labs. 2.Verify the default sorting of products . 3.Select a different sorting option from the available dropdown | link:https://www.saucedemo.com/ | User Should able to see product page | User Should able to see product page | High | High | Durgesh kr Prajapati | pass | 15/10/2024 | 15/10/2024
UserID:standard_user Password:secret_sauce

## Defects
TE Name | Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
Durgesh Kumar Prajapati | DEF001 | Saucedemo | Click on login button | REQ001 | TC_03 | Click on login button | Verify the behavior of the login functionality by enter a lowercase character of username and correct password | Click on login button don't opening to the product page | Low | Medium | Durgesh Kumar Prajapati
Durgesh Kumar Prajapati | DEF002 | Saucedemo | Click on login button | REQ001 | TC_10 | Click on login button | Verify the behavior when a user enter correct username and password should be empty | Click on login button don't opening to the product page | High | High | Durgesh Kumar Prajapati
Durgesh Kumar Prajapati | DEF003 | Saucedemo | Click on login button | REQ001 | TC_13 | Click on login button | Verify the behavior when a user enter correct username and password without speical character | Click on login button don't opening to the product page | Medium | High | Durgesh Kumar Prajapati
Durgesh Kumar Prajapati | DEF004 | Saucedemo | Click on login button | REQ001 | TC_14 | Click on login button | Verify the behavior when a user enter correct username and password should be only 8 character | Click on login button don't opening to the product page | Low | Low | Durgesh Kumar Prajapati

## Defect_Snapshots
Defect ID | Test Case ID | Failed Screenshots
DEF001 | TC_03
DEF002 | TC_10
DEF003 | TC_13
DEF004 | TC_14

## Test excution details
Test Case ID | Test Case Name | Screenshots | TestCase Execution Date | TestCase Execution Start Time | TestCase Execution END Time
TC_03 | Verify the login functionality when a user enter a lowercase character of username and correct password |  | 14/10/2024 | 10.15am | 10.18am
TC_10 | Verify the login functionality correct username and password should be empty |  | 15/06/2024 | 11.38am | 11.42am
TC_13 | Verify the login functionality correct username and remove the special character from the password |  | 15/10/2024 | 01.00pm | 01.04pm
TC_14 | Verify the login functionality correct username and user enter password only 8 character |  | 15/10/2024 | 03.05pm | 03.08pm

## Story_Point_Effort_and_Reason
User Story1-Durgesh Kumar Prajapati
Project Name :- | Saucedemo
Story Point :- | 2
Reason for story point :- | User is able to click on login button and to see home page
Efforts(in hours) :- | 5
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1 Raising Bugs:1

## Test report
SNO | TE NAME | TOTAL TEST CASE | PASS | FAIL | BLOCKERS | NOT EXECUTED | PASS RATIO (%) formula use : D2/C2*100 | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | Durgesh kr prajapati | 15 | 11 | 4 | 0 | 0 | 73 | 0 | 0 | 15 | 4
2 | Durgesh kr prajapati | 9 | 8 | 1 | 0 | 0 | 88 | 0 | 0 | 9 | 1
TOTAL